## Instructions
IT Project Plan | INSTRUCTIONS
MDE_IT Project Plan.xls
Description: Use this simple Excel spreadsheet to help you develop a project plan. You don't
have to be a Microsoft Project expert to develop great project plans. In fact, you may find this tool to be
more acceptable to most of your clients that don't have M/S Project. I have used this template
hundreds of times over that past 25 years, even before electronic spreadsheets were available.
There are two blank templates in the Project tab and an example is included in the Example tab. If you want
a more detailed plan example, refer to the IT Systems Conversion Plan tool in this ToolKit.
Project management is discussed in much more detail in the IT Project Management book of the
IT Manager Development Series. Additional information is at www.mde.net/cio.
Instructions:
The columns are:
- Line Number (for reference as needed; there are up to 25 tasks per page)
- Task (individual tasks to be completed. It helps to list them by major groups (Ordering, Training, etc.)
- Responsibility (initials of the responsible party. This person is who the project team looks to for
completing the task, not necessarily who actually completes the task)
- Months
- Five columns for every month in case of 5 weeks in the month
- I use the Friday, week ending date - this helps me know what needs to be accomplished by the
end of the work week.
Project Plan - Initial Setup:
1. Fill in the Project Name
2. Fill in the Project Manager name and contact information (E-mail, phone number, etc.)
3. Fill in the month at the top of the columns (JAN, FEB, AUG, etc.)
4. Fill in the week ending dates for each weekly column. There are five columns to handle 5-week months.
5. List the tasks and responsible person for each task.
6. Place a slash mark "/" in the cell of the week that the task should be completed.
7. List the resource participants and their initials at the bottom of the first page for reference.
Project Plan - Update Steps:
1. For each task that is completed, change the slash to an "X"; move the slash mark as needed if certain
tasks need to move out.
Other:
- To add additional sheets, simply cut and paste an entire page.
- Different printer models will print EXCEL spreadsheets differently. You may have to play with the
spreadsheet a bit to get the entire page to print on a single 8x10 piece of paper

## Project Plan Template
MDE Enterprises, Inc.
2011-09-18
Project: |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5
Project Manager:
| ACTIVITY | Resp.
1 | [7 empty] | 1
2 | [7 empty] | 2
3 | [7 empty] | 3
4 | [7 empty] | 4
5 | [7 empty] | 5
6 | [7 empty] | 6
7 | [7 empty] | 7
8 | [7 empty] | 8
9 | [7 empty] | 9
10 | [7 empty] | 10
11 | [7 empty] | 11
12 | [7 empty] | 12
13 | [7 empty] | 13
14 | [7 empty] | 14
15 | [7 empty] | 15
16 | [7 empty] | 16
17 | [7 empty] | 17
18 | [7 empty] | 18
19 | [7 empty] | 19
20 | [7 empty] | 20
21 | [7 empty] | 21
22 | [7 empty] | 22
23 | [7 empty] | 23
24 | [7 empty] | 24
25 | [7 empty] | 25
REMARKS:
IT manager tools to achieve more - www.itmanagerinstitute.com
MDE Enterprises, Inc.
2011-09-18
Project: |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5
Project Manager:
| ACTIVITY | Resp.
1 | [7 empty] | 1
2 | [7 empty] | 2
3 | [7 empty] | 3
4 | [7 empty] | 4
5 | [7 empty] | 5
6 | [7 empty] | 6
7 | [7 empty] | 7
8 | [7 empty] | 8
9 | [7 empty] | 9
10 | [7 empty] | 10
11 | [7 empty] | 11
12 | [7 empty] | 12
13 | [7 empty] | 13
14 | [7 empty] | 14
15 | [7 empty] | 15
16 | [7 empty] | 16
17 | [7 empty] | 17
18 | [7 empty] | 18
19 | [7 empty] | 19
20 | [7 empty] | 20
21 | [7 empty] | 21
22 | [7 empty] | 22
23 | [7 empty] | 23
24 | [7 empty] | 24
25 | [7 empty] | 25
REMARKS:
IT manager tools to achieve more - www.itmanagerinstitute.com

## Example
MDE Enterprises, Inc.
| 2011-09-18 | Example
Project: New PC Setup (Project Example) | [5 empty] | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY
Proj. Mgr.: Roger Rabbit
| ACTIVITY | Resp. | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25
1 | I. Order | [22 empty] | 1
2 | A. Order PC, monitor, and printer | BB |  | X | [19 empty] | 2
3 | B. Order M/S Office & Marketing Database Software | BB |  | X | [19 empty] | 3
4 | C. Order paper, special forms, diskettes | BB |  | X | [19 empty] | 4
5 | [23 empty] | 5
6 | II. Installation | [22 empty] | 6
7 | A. Install PC & monitor | YS |  |  |  | X | [17 empty] | 7
8 | B. Load software | YS |  |  |  | X | [17 empty] | 8
9 | C. Install printer | YS |  |  |  | X | [17 empty] | 9
10 | [23 empty] | 10
11 | III. Training | [22 empty] | 11
12 | A. MS Office training | RR | [6 empty] | / | [14 empty] | 12
13 | B. Marketing Database Software training | MM | [7 empty] | / | [13 empty] | 13
14 | [23 empty] | 14
15 | IV. Client Prospect Database | [22 empty] | 15
16 | A. Create prospect database | WC | [8 empty] | 2: /; 9: ---; 16: / |  |  |  |  | 16
17 | B. Test mass mail merge capabilities of database with MS WORD document | WC | [21 empty] | 17 | bar: 16
18 | C. Create prospect letter | WC | [21 empty] | 18 | bar: 16
19 | D. Create mass mail to top 1000 prospects | WC | [21 empty] | 19 | bar: 23
20 | [23 empty] | 20
21 | [23 empty] | 21
22 | [23 empty] | 22
23 | [23 empty] | 23
24 | [23 empty] | 24
25 | [23 empty] | 25
REMARKS:
BB - Bugs Bunny
YS - Yosemite Sam
RR - Roger Rabbit
WC - Wylie Coyote
MM - Mickey Mouse (Outside Vendor of Marketing Software)
IT manager tools to achieve more - www.itmanagerinstitute.com